## Sheet1
Learning Recovery & Alternative Dispute Resolution Grant Actvities 2021-2022
Staff Increases
Grant | Position | FTE | Status | Implemenation Progress |  |  | Anticipated Cost
Learning Recovery Grant (6537) | New OT position | - 2 days/ week | Filled | Complete |  |  | 30094.86
Learning Recovery Grant (6537) | New SLP position | Full time | Vacant |  |  |  | 48495
Learning Recovery Grant (6537) | New Behavior Support Specialist | 1 full time (7 hour day) | Filled | Complete |  |  | 19984.11
Learning Recovery Grant (6537) | New Mental Health Clincian | 15 hours/ week | Filled | Complete |  |  | 25827
Learning Recovery Grant (6537) | After School Tutoring | up to 4-5 hours/week | 1 program | 1 in progress |  |  | Will be calculated at the end of the fiscal year.
Learning Recovery Grant (6537) | After School Social Skills | up to 4-5 hours/week | 1 after school program | 1 program in progress
New Curricuum
Grant | Curriculum | Schools | Status | Implemenation Progress
Learning Recovery Grant (6537) | Sonday System- TK-8 Intervention and supplemental materials | Capay, Hamilton, Lake, Orland (Mill, Fairview, Ck Price), Princeton, Willows (Murdock, WIS) | Ordered & Recived | Teacher PD scheduled for December | Implementation by January 2022 | Complete | 28483.49
Materials
Grant | Materials | Programs
Learning Recovery Grant (6537) | Alternative and Augmentative Communication Assessment Kit | Avalaible to all SLPs in the county for assessments | Speciality Materials List Being Created | Cost pending
Learning Recovery Grant (6537) | Regional Program Supplies
Professional Development
Grant | Activity | Staff Particpating | Schedule |  | Implemenation Progress
Federal ADR (3395) | Alternative Dispute Resolution Training Series - 5 sessions | 23 (OUSD & GCOE) | 5 trainings |  | 4 sessions complete 1 date in April |  | 9000
State ADR (6536) | Special Education Discipline for GE Administration | District GE Administrators | March 29 8:30-10:30 |  | Session complete - 10 participants |  | 580
State ADR (6536)
State ADR (6536) | Pepperdine Straus Insitute Medication Training | 1 OUSD & 3 GCOE SPED Admin Completing | December, April & June Cadre |  | 2 in December, 1 in April, 1 in June |  | 20000
Learning Recovery Grant (6537) | Apraxia Assessment & Serivces | All SLPs | Training Complete 48 SLPs particpated |  | Completed |  | 3000
Learning Recovery Grant (6537) | Trauma Informed Teaching- in person | All staff | 2022-08-01 | BCOE provided free of cost
Learning Recovery Grant (6537) | Discrete Trial Teaching/Curriculum | Preschool Staff | August Sessions plus 2 coaching sessions in class |  | Needs assessment scheduled for April
Learning Recovery Grant (6537) | Paraprofessional Training Series | Open to all paraprofessionals | TBD due to sub issues
Learning Recovery Grant (6537) | Restorative Practices - in person | High School Teachers (GCOE and OUSD), Osprey Teacher, School Psychologists, sped administrators | 4 dates March & April 3:30-5:30 | Stipends for 23 special education through GCOE/OUSD | Training series complete ~12 particpants |  | Training Cost-$2,999.52
Learning Recovery Grant (6537) | Special Education Assessments Legal Update-zoom | School Psycholgosits and SPED Admin (GCOE & OUSD) | March 29 3:00-5:00 | 25 Staff | Completed |  | 1220
Learning Recovery Grant (6537) | Secondary Trauma Workshops | Mental Helath Clincians, School Psychologists | Once a month, on going |  | ongoing |  | 825
Parent Outreach/Child Find
Grant | Activity | Progress |  | Implementation
State ADR (6536) | Annual Event Celebrate Inclusion Pumpkin Run 5k | Established agreement with Rowell Family Empowerment for the event MOU in Development/ Creating Event Board to meet in Jan 2022 Board met to review date, times, theme, event route and evaluating resources in the county. |  | Board met: updates DJ secured, route is being secrued with OPD, banner on 32 has been reserved, FFA willing to loan pumkins for decoration, further tasks distributed Next meeting May 25 |  |  | $5,000 Budgeted $0 has been spent
State ADR (6536) | ChildFind | Developing Brochures and Social Media Posts for the Community | Materials go to SPED Cabinet for approval Cabinet met for intial review, final review 1/21/22. SELPA Governance review at February SELPA governance meeting. | Governance Review February SELPA agenda -approved, collecting school logos - final logo received in April, scheduled for printing and discemination May
State ADR (6536) | Parent Trainings | Partnering with Rowell to Establish Dates & Topics | Survey Parents for Dates/Times
How much has
|  |  | Total | been spent | Balance
| Key: | ADR Grant | 104755 | 40950.35 | 63804.65
|  | Learning Recovery Grant | 471398 | 98519.02 | 372878.98